## About
About
www.solvermax.com
Key
Data
Constant
Highlight
Error
Solver variable
Pasted values
Version
v 1.0
2021-12-02
Purpose
This workbook contains an example optimization model and associated analysis. The purpose is to illustrate the design and use of optimization models in Microsoft Excel, using the Solver and/or OpenSolver add-ins.
This workbook should be read in conjunction with the articles at:
http://www.solvermax.com
Sheets
This workbook contains the following sheets:
'About': This sheet, used to document the workbook.
'Model n': One or more optimization model worksheets.
'Analysis': Insights gained from using the model.
'Control': Values used to control the workbook.
Disclaimer
This workbook is presented on an as is basis for illustrative purposes only and should not be relied upon for making financial, legal or any other commitments. Solver Max will accept no responsibility or liability for any errors or omissions.
Copyright
This workbook is © Copyright 2021 Solver Max.
Solver Max retains copyright of this workbook.

## Model 1
Model 1: Project crashing
Assumptions | [6 empty] | Description
Duration
48
Duration and cost for each task
Task | Activity | Duration (days) |  | Cost ($/day)
|  | Normal | Crash | Normal | Crash
A | Engagement | 5 | 4 | 72 | 440
B | Requirements | 9 | 4 | 996.44 | 188.8
C | Design | 9 | 4 | 326 | 138.32
D | Tech documentation | 17 | 15 | 868 | 3689
E | Test design | 12 | 7 | 50.5 | 178.8
F | Specification | 10 | 7 | 531 | 336.3
G | Build | 17 | 15 | 936 | 6084
H | User documentation | 5 | 4 | 2611.2 | 6528
I | Unit testing | 19 | 17 | 529 | 3068.2
J | Test documentation | 7 | 5 | 885.71 | 372
K | Revision | 20 | 14 | 476 | 412.53
L | Approval | 1 | 1 | 960 | 0
M | User training | 8 | 6 | 663 | 1326
N | Integration testing | 15 | 11 | 754.13 | 949.53
O | Deployment | 6 | 5 | 950 | 3800
Total |  | 160 | 119
Intermediate calculations
Path steps: Task name | [6 empty] | Path steps: Task number
Path | Task paths | [5 empty] | Path | Task paths
| Step 1 | Step 2 | Step 3 | Step 4 | Step 5 | Step 6 |  | Step 1 | Step 2 | Step 3 | Step 4 | Step 5 | Step 6
1 | A | B | F | L | O |  | 1 | 1 | 2 | 6 | 12 | 15 | x
2 | A | B | K | L | O |  | 2 | 1 | 2 | 11 | 12 | 15 | x
3 | A | B | K | M | O |  | 3 | 1 | 2 | 11 | 13 | 15 | x
4 | A | C | G | K | L | O | 4 | 1 | 3 | 7 | 11 | 12 | 15
5 | A | C | G | K | M | O | 5 | 1 | 3 | 7 | 11 | 13 | 15
6 | A | D | K | L | O |  | 6 | 1 | 4 | 11 | 12 | 15 | x
7 | A | D | K | M | O |  | 7 | 1 | 4 | 11 | 13 | 15 | x
8 | A | D | H | J | M | O | 8 | 1 | 4 | 8 | 10 | 13 | 15
9 | A | E | J | M | O |  | 9 | 1 | 5 | 10 | 13 | 15 | x
10 | A | E | I | M | O |  | 10 | 1 | 5 | 9 | 13 | 15 | x
11 | A | E | I | N | O |  | 11 | 1 | 5 | 9 | 14 | 15 | x
Variables | [6 empty] | Result
Crash decisions | [6 empty] | Path steps: Result | [7 empty] | Objective function
Task | Task paths Step 1: Activity; Task paths Step 2: Crash days; Task paths Step 4: Result | Path | Crashed duration of task paths (days) | [6 empty] | Plan | Cost ($)
|  | Selected | Limit | Cost | Days |  |  | Step 1 | Step 2 | Step 3 | Step 4 | Step 5 | Step 6 | Total | Normal | 110948.88
A | Engagement | 1 | 1 | 440 | 4 |  | 1 | 4 | 9 | 10 | 1 | 5 | x | 29 | Crash | 25019.84
B | Requirements | 0 | 5 | 0 | 9 |  | 2 | 4 | 9 | 14 | 1 | 5 | x | 33 | Total | 135968.72
C | Design | 5 | 5 | 691.6 | 4 |  | 3 | 4 | 9 | 14 | 6 | 5 | x | 38
D | Tech documentation | 0 | 2 | 0 | 17 |  | 4 | 4 | 4 | 15 | 14 | 1 | 5 | 43
E | Test design | 5 | 5 | 894 | 7 |  | 5 | 4 | 4 | 15 | 14 | 6 | 5 | 48
F | Specification | 0 | 3 | 0 | 10 |  | 6 | 4 | 17 | 14 | 1 | 5 | x | 41
G | Build | 2 | 2 | 12168 | 15 |  | 7 | 4 | 17 | 14 | 6 | 5 | x | 46
H | User documentation | 0 | 1 | 0 | 5 |  | 8 | 4 | 17 | 5 | 7 | 6 | 5 | 44
I | Unit testing | 0 | 2 | 0 | 19 |  | 9 | 4 | 7 | 7 | 6 | 5 | x | 29
J | Test documentation | 0 | 2 | 0 | 7 |  | 10 | 4 | 7 | 19 | 6 | 5 | x | 41
K | Revision | 6 | 6 | 2475.18 | 14 |  | 11 | 4 | 7 | 19 | 13 | 5 | x | 48
L | Approval | 0 | 0 | 0 | 1
M | User training | 2 | 2 | 2652 | 6
N | Integration testing | 2 | 4 | 1899.06 | 13
O | Deployment | 1 | 1 | 3800 | 5
Total |  | 24 | 41 | 25019.84 | 136
Situation
We have a baseline project plan. The project consists of 15 tasks, with durations that range from 1 day to 20 days per task. Given the interactions between tasks, especially the dependency requirements, the baseline project plan has a duration of 65 days.
Most tasks can be completed faster by deploying additional resources, which would incur additional cost. The process of reducing the duration of a project, by deploying additional resources, is called "project crashing".
Our objective is to find, for a specified project duration, the lowest cost project plan.
Formulation
We want to look at reducing the duration of some tasks to assess the effect on the overall project duration. To enable this assessment, we need to define all potential paths through the project plan. For this project, there are 11 paths, each of which includes up to 6 tasks.
Each reduction in a task's duration incurs a cost. We want to minimize total project cost. The variables represent the number of days to reduce each task, subject to an upper bound on the reduction for each task. All potential paths must have a duration less than or equal to the specified duration.
Solution
From the baseline project duration of 65 days, we can find the minimum cost for each duration down to 48 days. Less than 48 days is not feasible, given the crash duration for the tasks. The best choice of duration, between 48 and 65 days, is a judgement that will need to be made.
References
Li, K., Shao, B., & Zelbst, P. (2012). "Project crashing using Excel Solver: A simple AON network approach". International Journal of Management & Information Systems – Second Quarter 2012, Volume 16, Number 2, pp. 177-182.

## Analysis
Supporting analyses
Description
Trade-off between project cost and duration
Duration | Cost ($) | Change ($) | Change (%)
48 | 135968.72 | 25019.84 | 22.55%
49 | 128935.19 | 17986.31 | 16.21%
50 | 121901.66 | 10952.78 | 9.872%
51 | 118101.66 | 7152.78 | 6.447%
52 | 116596.86 | 5647.98 | 5.091%
53 | 115092.06 | 4143.18 | 3.734%
54 | 114500.73 | 3551.85 | 3.201%
55 | 113909.4 | 2960.52 | 2.668%
56 | 113318.07 | 2369.19 | 2.135%
57 | 112878.07 | 1929.19 | 1.739%
58 | 112465.54 | 1516.66 | 1.367%
59 | 112053.01 | 1104.13 | 0.9952%
60 | 111640.48 | 691.6 | 0.6234%
61 | 111502.16 | 553.28 | 0.4987%
62 | 111363.84 | 414.96 | 0.374%
63 | 111225.52 | 276.64 | 0.2493%
64 | 111087.2 | 138.32 | 0.1247%
65 | 110948.88
57
The baseline project duration is 65 days. As we reduce the duration, the optimal project cost increases. The best trade-off between cost and duration is a judgement that will need to be made.
Provided sufficient budget is available, a potentially good trade-off is to reduce the project duration to 53 days. This reduction of 12 days (18.5%), compared with baseline, incurs a $4,143 (3.7%) cost increase. Duration reductions to less than 53 days incur steep increases in cost.
Given the maximum crash days for each task, the shortest possible project duration is 48 days. Reducing the project duration by 17 days (26.2%) incurs a $25,020 (22.6%) cost increase.

## Control
Workbook control
Constants | Notes
Boolean
TRUE
FALSE
Derived values
Named ranges
To make the Solver dialog easier to understand, the model's data, formulae, and variables are defined as range names that use the following convention:
- Data range names start with d.
- Formulae range names start with f.
- Variable range names start with v.